## V2 Council adoption
SNOWY VALLEYS COUNCIL ROAD TO SUSTAINABILITY PLAN 2023/24
The table below provides a summary of the key actions Council intends to undertake to achieve its objective of delivering sustainable best value to the community.
This list will be reviewed and updated regularly and reported to Council together with updates to the Operational Plan.
No. | Subject | Action | What? | Project Sponsor | When? | Project Sponsor2 | Updated Comment
1 | IP&R | Prepare SRV | Prepare new SRV and scenario model in LTFP Develop engagement plan Deliver community engagement Submit to IPART | DCC | Application completed by Febuary 2024 | Director Community & Corporate | Febuary 2024
2 | IP&R | Determine process for new suite of IP&R documents | Revise the structure of Council's Delivery Program to facilitate better strategic planning, aligning Council's activities with budgets Coordinate the preparation of the new suite of IP&R documents with key stakeholders | DCC | New term of Council | Executive Leadership Team | 2025
3 | IP&R | Establish Integrated Water Cycle Management Strategy | Finalise a new integrated Water Cycle Management Strategy for the SVC local government area including strategic planning for water supply and wastewater services, financial planning etc. | DIW | by December 2025 | Director Infrastructure & Works | Funding agreement signed and Public Works appointed to undertake project with a December 2025 completion date.
4 | Funding and revenue | Manage Reserves | Update reserves policy with view to sustainability, model reserve movements over the next 10 years and propose alternative funding models Utilise developer contributions to fund projects and upgrades | GM | by September 2021 and ongoing | Director Community & Corporate Manager Finance Exec Mgr Growth & Development | Ongoing
5 | Funding and revenue | Review fees and charges | Review of all fees and charges and benchmark against other Councils Establish the full cost of all services and raise fees and charges where applicable until they cover costs while considering community service obligations Council makes fully informed decisions about subsidising services | DCC | progressively over 3 years (2021-2023) | Executive Leadership Team | Ongoing
6 | Funding and revenue | Continue to pursue operating grants | Continue to pursue operational grant funding Review all new and upgrade proposals for sustainability criteria prior to funding submission and clearly document this in submissions and project plans | GM | Ongoing | Executive Leadership Team | Ongoing
7 | Funding and revenue | Pursue commercial business opportunities | Proactively pursue commercial opportunities to realise economies of scale and generate commercial returns to support other areas of Council Decline commercial works that don't return profit margins at a level set in SVC's commercial works or other relevant strategy | GM | Ongoing | Executive Leadership Team | Ongoing
8 | Operational Expenditure | Review Council's procurement processes | Review procurement framework and implement improved procurement processes, including utilising enterprise system capabilities | DCC | by December 2024 | Executive Leadership Team
9 | Operational Expenditure | Reduce operational employee costs | Evaluate and review all vacancies with a view to operational savings upon review of service levels Reduce employee costs through a review of workforce numbers, work patterns, benefits and restrictions around workforce and wages Ensure employee costs are capitalised where appropriate | GM | ongoing cost savings reviewed when vacancy arises. | Executive Leadership Team | Ongoing - 5 positions recetnly removed from the structure as vacancies occur each position will be critically examined to determined whether the position needs to be retained and/or redesigned.
10 | Operational Expenditure | Reduction of excess leave balances | Set excess long service leave reduction target (>20%) for 2021/22 Set annual leave and Toil/RDO balance reduction target (>10%) for 2021/22 | GM |  | Executive Leadership Team | Ongoing
11 | Operational Expenditure | Allocate overheads and direct costs | Review allocation of overheads and direct costs to better reflect actual costs of services Allocate appropriate overheads across the entire organisation, including capital projects and commercial works - implemenation depending on enterprise system review progress and improvements | DCC | by June 2024 | Manager Finance | Under review
12 | Operational Expenditure | Capture savings | Identify operational cost saving opportunities and efficiencies, capture savings rather than re-investing Renegotiate supplier contracts (enterprise system, IT, utilities, phones, fleet, waste, project management etc.) with a view to cost savings Set savings targets (>2.5%) for individual managers and coordinators | DCC | Ongoing | Executive Leadership Team | Ongoing - contracts and licencing reviewed when due for renewel
13 | Operational Expenditure | Review the use of consultants | Ensure use of consultants is efficient and effective | GM | Ongoing | Executive Leadership Team | Ongoing
14 | Cash | Optimise working capital | Optimise working capital by maximising collections, timely billing, timely recouping of expenditure, extension of creditor payment terms to commercial terms and reduction of payment cycle frequency | GM | Ongoing | Manager Finance | Ongoing
15 | Cash | Maximise Investment Returns | Maximise investment returns balanced against risk and policy requirements | GM | Ongoing | Manager Finance | Ongoing
16 | Projects, programs, capital works | Review Advocacy Plan | Review current advocacy priorities in the context of the Sustainability Plan | GM | by Dec 2024 (new Council) | General Manager
17 | Projects, programs, capital works | Enable Program Management Group | Enable fully functional PMG, including systems and processes | DCC | by June 2021 | Executive Leadership Team | Completed
18 | Projects, programs, capital works | Implement whole of life costing model | Consistently follow Council’s gated project assessment framework and implement compulsory whole-of-life costing model | GM | by June 2022 | Executive Leadership Team | Ongoing
19 | Projects, programs, capital works | Review and reduce current project delivery program | Review projects and programs based on capacity to deliver | GM | Ongoing | Executive Leadership Team
20 | Projects, programs, capital works | Prioritise capital renewal projects | Restructure the capital projects plan around essential assets | DIW | Ongoing | Executive Leadership Team | Ongoing
21 | Service Levels | Assess holding costs | Assess holding costs of all non-income producing assets vs. current and future needs and consider divesting where financially unsustainable | DIW | Ongoing | Executive Leadership Team | Ongoing
22 | Service Levels | Prepare Service Management Plans (SMP) | Finalise SMPs for all Council services Review and report on alternative delivery options for ALL services | GM | Draft SMPs by June 2021 progress report by September 2021 and ongoing quarterly | Executive Leadership Team | Ongoing reviewed by Dec 2024
23 | Service Levels | Divest services | Divest low-value services Prioritise service delivery of those services that promise the highest gains or savings | GM | by June 2022 | Executive Leadership Team | Ongoing
24 | Service Levels | Define maintenance management systems | Undertake analysis of maintenance systems and assess opportunities for improvement, advancement and integration Finalise maintenance management systems for transport, drainage, open space and facilities asset classes Establish business case for integration of service management into Council's enterprise system Effect integration of system into Council's enterprise maintenance module - pending continuous review of Council's enterprise system | DCC | by December 2023 | Director Infrastructure & Works | Reviewed date 30 June 2025
25 | Service Levels | Needs analysis for recreational activities and community buildings | Undertake a needs analysis for recreational activities and community buildings, considering asset renewal needs, potential new/upgrade assets to meet community needs, opportunities for disposal etc. as part of preparing the Open Space and Facilities SMP | DIW | by December 2022 | Executive Leadership Team | Reviewed date 31 December 2024
26 | Service Levels | Improve data collection | Improve data collection about effectiveness, efficiency of services and other key performance drivers to allow for informed decision-making Focus reporting on operating performance ratios, own-source revenues and long-term sustainability | GM | by June 2022 | General Manager | Ongoing
27 | Service Levels | Empower community groups | Enable community groups to deliver projects and events that sit outside Council's responsibility | GM | by December 2021 | Executive Leadership Team | Ongoing
28 | Service Levels | Digital transformation | Continue to identify improvement opportunities and deliver digital transformation projects for internally and for community-facing services | DCC | Ongoing quarterly progress report | Executive Leadership Team | Ongoing
29 | Strategy | Review Enterprise System | Review utilisation of enterprise system and system modules and how they can support sustainability targets Establish business case for continuation of Council's enterprise system (or otherwise), including resourcing Reconsider all Council systems, reduce systems in use and integrate with Council's enterprise system | DCC | Ongoing | Director Community & Corporate
30 | Strategy | Continue to establish strategic business plans | Strategic business planning for all business units including sustainability proposal | GM | phase 1 - by December 2024 phase 2 - December 2025 | General Manager
31 | Strategy | Define funding strategy | Define funding needs and develop a funding strategy that includes operational and capital funding and delivers on Council sustainability targets | DCC |  | Executive Leadership Team | By 31 March 2024 and then ongoing
32 | Strategy | Culture transformation | Continue to focus organisation on positive work culture and employee engagement concentrating on sustainability, business improvement, alternative ways of working, performance management framework, accountabilities and link to strategic plans | DCC | Ongoing | Director Community & Corporate | Ongoing - Staff Culture Survey to be completed during next term of Council once merger issue resolved.
33 | Strategy | Culture transformation | Develop a program of initiatives and a change management program | DCC |  | Executive Leadership Team | To be completed by 31 December 2024
34 | Strategy | Review Council's overall risk profile | Utilise Enterprise Risk Management Framework (ERMF) to assist in identifying and exploiting opportunities for new or increased revenue streams and expenditure reductions | DCC | Ongoing progress report by June 2022 | Director Community & Corporate | Ongoing